## Goal 1A
Goal 1A- Continue management of solid waste through reduction of paper usage
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Implement University wide policy to require all course syllabi to be available electronically | Goal 3 | Academic Affairs | Fall 2020 - Fall 2022 | Draft a general policy in a General Education workgroup | 100 percent of full and part-time faculty using electronic syllabi.
Approval of Gen Ed curriculum committee, Faculty Senate, and Provost
Approval by University Council and Cabinet
New policy communicated to all Faculty members
New policy added to University website
Post all course and supplemental materials in Blackboard | Goal 3 | Academic Affairs | Fall 2020 -Fall 2022 | Draft a general policy in a General Education workgroup | 100 percent of Academic Departments posting all materials on Blackboard.
Approval of Gen Ed curriculum committee, Faculty Senate, and Provost
Approval by University Council and Cabinet
|  | DIT |  | New policy communicated to all Faculty members
New policy added to University website
University-wide implementation of electronic forms, electronic signature, and workflow to replace paper-based processes (primarily HR) | N/A | Human Resources | Summer 2020 – Summer 2023 | Identify all sources of requests that use paper forms | Reduction in use of paper-driven processes by 75%.
Determine vendor pool, evaluate offerings
Pilot engagement with selected vendor
Form Selection Committee
Evaluation and recommendations from Selection Committee
|  | DIT |  | CPIC process (DIT)
Acquire, implement, and manage solution
Create campaign to notify campus community of this change
Digital archiving of HR documents | Goal 1C | Human Resources | Spring 2021-Spring 2022 | Identify all documents that need storage and archiving | Digital archival of 80% of stored HR documents
Determine vendor pool, evaluate offerings
Coordinate digitalization of documents
Documents scanned are stored for secure destruction
Documents shredded

## Goal 1B
Goal 1B- Continue management of solid waste through reduction of food waste and addressing food insecurity
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Reduce food waste from catered events | Goal 3 | Auxiliary (Dining) Services | Spring 2021 – Fall 2021 | Identify text alert software that allows students to sign up to be notified of catering events that have food remaining at the conclusion of the event | Implementation and accuracy of technology for students to sign up
|  |  |  | Develop steps & guidelines for event holder to communicate food overage to students at the conclusion of the event | Number of student participators signed up
|  | DIT |  | Develop tool for measuring student participation in program
Work with DIT
Expand sustainable options in the food pantry | N/A | Health & Wellness | Spring 2020 – Spring 2021 | Communicate with distributors to offer more fresh vegetables and fruits | Number of visitors to pantry
|  |  |  | Work with retailer to obtain recycled bags and distribute recycled bags for food items. | Number of bags distributed in grab and go.
Implement Sustainable To Go Program | Goal 3 | Auxiliary (Dining) Services | Summer 2020 – Fall 2021 | Increase meal plan purchases for non-required meal plans (faculty/staff, and commuters) | Increase program participation by 2.5% of total meal plan participation each semester
|  |  |  | Work to increase carry out options | Increase non-required meal plan purchases by 10 meal plans each semester
Increase marketing efforts
Allow students who may be suffering from food insecurity to obtain free meals on campus | N/A | Auxiliary (Dining) Services | Fall 2021 - Spring 2022 | Create process to identify students who suffer from food insecurity
Create system

## Goal 1C
Goal 1C- Continue management of solid waste through increased recycling and/or reusing
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Collaborate with Follett to increase sustainability practices in campus bookstore | N/A | Auxiliary Services | Fall 2021 – Fall 2022 | Implementation of “Please Don’t Take A Bag Program” | Decrease plastic bag usage by 5% in year one and 10% in year 2
|  |  |  | Offer reusable bags for purchase | Number of students participating in the buyback program increased by 3% year one and 5% year two.
|  |  |  | Use recyclable and biodegradable bags | Digital book options increased by 3% year one and 5% year two.
|  |  |  | Enhance the marketing of the buyback book program | A minimum of 10 eco-friendly gift and clothing items offered at the bookstore annually
|  | Procurement |  | Increase digital book options | Electronic battery drop off station in bookstore
Increase eco-friendly gift and clothing items
Collaborate with Procurement Services to provide electronic battery drop off in Bookstore
Create a Recycling task force | Goal 3 | C4 | Spring 2021 | Create a statement of work to include the problem and timeline | Decrease in types of recycle bins across campus
|  |  |  | Form task force through recommendation from VP, other cabinet members, C4 and Student Life | Decrease in amount of landfill waste from BSU over time
|  | Various departments |  | Hold meetings to gather recommendations | Increase in amount of recycable items
Form and submit proposal
Place more recycle bins in the Residence Halls. | Goal 3; Goal 5 | Residence Life | Fall 2022 | Take recommendations from task force on recycle bins for rooms and in common areas | Number of recycle bins in residence halls
Purchase recycle bins for residence halls
Renegotiate ABM contract in residence halls to allow for increase in bin collection and proper hauling.
Expand Book Recycling | N/A | Procurement | Spring 2021- Fall 2021 | Identify locations for collection points and persons responsible for collection | 50% increase in recycled books after 2 years
|  | Auxiliary Services |  | Purchase collection bins (if necessary)
|  | Academic Affairs |  | Set up a location in the residence halls and academic buildings to collect unwanted books for recycling.
Expand ink recycling program | N/A | Procurement | Spring 2021 | Identify locations for collection points and persons responsible for collection | 25% increase in ink cartridges recycled
Purchase collection bins (if necessary)
Set up ink Recycling boxes through out the campus and keep track of the usage.
Create Dorm Mania program | Goal 3 | Residence Life | Spring 2021- Fall 2021 | Research and review similar programs at other institutions | Number of items donated
|  | Facilities Management |  | Create student based team to design and coordinate program | Number of students who participate in 1) donation, and 2) receiving items
Establish general rules, list of items and come up with incentives, design t-shirts etc for the team
|  | C4 |  | Contact local agencies such as Goodwill and Best Buy to team with for disposal of clothing & e-cycled items
Create flyers and social media buzz of items that can be donated during move-out
|  | Student Life |  | Coordinate with Facilities Management on storage of items

## Goal 2
Goal 2- Increase energy efficiency and conservation
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Continue to retrofit building common areas with LED lighting | N/A | Facilities Management | Spring 2020- Summer 2021 | Identify retrofit areas | Lowered utility bills.
|  |  |  | Purchase requisite number of bulbs | Decreased rate of Maintenance for lighting
Coordinate installation schedule with building occupants
Install bulbs/fixtures
Initiate program for installation of lighting sensors in common areas and hallways of residence halls | N/A | Residence Life | Fall 2025 | Assessment of the most frequently used rooms or spaces in the residence hall. | Areas complete with lighting sensors
|  | Facilities Management |  | Meeting with Facilities Management to ensure process of completion
Obtain quotes from a contractor to complete the work.
Coordinate and installation of lighting sensors
Undergo campuswide project to replace old and leaky roofs of several buildings | RESILIENCE | Facilities Management | Summer 2020- Fall 2020 | Survey and access the existing roof | Replaced roofs
|  |  |  | Provide specifications for design | Lowered utility bills due to improved efficiency
Roofing contractor to remove existing roof
Install new roof

## Goal 3
Goal 3- Foster sustainable behavior through curriculum and training, community engagement, awareness activities and communications enhancement
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Incorporate Faculty Institute Presentation on BSU’s Sustainability Efforts | N/A | Academic Affairs | Spring 2021-Fall 2021 | Establish a partnership between C4 and CETL; | Faculty Survey
Explore speakers and workshops options;
Work with Academic Affairs to place presentation/s on schedule
Implement the option.
Create Sustainability Curriculum Component in Freshman Seminar (FRSE 101) | N/A | Academic Affairs | Fall 2021 | Assemble a development team | 100% of Freshman Seminar with Sustainability curriculum component
Develop module and pilot the module
Evaluate module
Evaluate Effectiveness of General Education’s Emerging Issue Component | N/A | Academic Affairs | Spring 2021-Spring 2022 | Establish a partnership between C4 and the General Education committee; | Report with recommendations
Determine who will perform studey and implement study
Report results and recommendations for improvement
Expand Earth Day celebration to include Residence Life & Student Life | N/A | Residence Life | Spring 2021 | Hold a comprehensive planning meeting | Number of participants
Design what program/s and/or event/s will look like
|  | C4 |  | Delegate responsibilities
Contact possible vendors & on campus partnerships
|  | Student Activities |  | Launch event
Initiate program for mandatory Sustainability training for all Residence Life staff | N/A | Residence Life | Fall 2021 | Communicate with other institutions that have or are putting this into practice | Training modules that are in conjunction with Resident Assistant training.
Form a team of Residence Life staff to plan and coordinate training as well as schedule
Add these responsibilities to the new Resident Assistant job description.
Get approval from VP of Student Affairs
Create a campus sustainability map | N/A | C4 | Fall 2020- Spring 2021 | Decide which projects should be highlighted on a campus map | Map produced and published on website
|  |  |  | Design key for map | Number of hits to this page on website
|  | URM |  | Consult with URM to create a digital map of sustainability features and projects across campus
Apply for full SGA status as campus organization for Student Green Ambassadors | N/A | C4 | Spring 2021 | Meet with Student Life on pros and cons of applying | Campus organization status granted
|  | Student Life |  | Apply for organization status
Develop sustainability branding and logo | N/A | CR | Summer 2021 | Solicit student idea designs for branding and logo | New branding
Meet with URM to propose designs
|  | URM |  | Get approval of designs
Enhance external community outreach efforts in sustainability | N/A | C4 | Spring 2021- Fall 2025 | Research local organizations, schools, and agencies active in environmental sustainability | Number of agencies worked with
|  |  |  | Respond to those orgs, schools, and agencies who have already reached out to partner with or sponsor BSU sustainability activities | Number of events including external partners
Cultivate relationships through communications, and work with on-campus groups to help collaborate with said agencies
Coordinate, plan, attend, participate in, invite and/or co-sponsor local and community climate change or sustainability related events, panel discussions, etc
Increase partnership opportunities in renewable energy for BSU community | N/A | C4 | Summer 2020- Fall 2025 | Promote the importance through social media & website the benefits of solar instatllation (and jobs) to BSU community | Number of students/recent grads working or interning in renewable energy field
Partner with on-campus groups/academies to recruit students in renewable energy and work with support staff and administration on leveraging available opportunities
Connect with solar employers or third party organizations to vet the available opportunities for students/recent grads
Assess and determine the fit for opportunities to match with the BSU community

## Goal 4
Goal 4- Reduce carbon footprint from transportation related emissions
Action | Supporting goal | Responsible dept/s | Time Frame | Tasks (description of steps): | Measure of success
Expand and Enhance BSU Bike Share Program | N/A | Auxiliary Services | Spring 2021 – Spring 2022 | Double the number of bicycles accessible for rental | Double the number of bicycles available on campus (goal of @ 30)
|  |  |  | Expand the number of locations on campus where bicycles can be rented to a minimum of 2 | Add rental locations to two locations
|  |  |  | Implement technology that eliminates the need to reserve a bike with a person through the creation of an online app | App created for reservation of bicycles and equipment
|  | Health & Wellness |  |  | Increased program participation for bike usage by students, faculty, and staff
Create virtual tour for Conference & Event Services to decrease in person visits | Goal 3 | Auxiliary Services | Fall 2020 | Collaborate with URM on scope of project | Virtual tour video complete
Identify key spaces on campus used for Conference & Events Services
Coordinate opportunity to capture various layouts of rooms
Identify independent videographer to film and edit the website
Add photos and videos to CES webpage
Increase permanent teleworking percentage of employees | N/A | Human Resources | Summer 2020-Summer 2021 | Communicate with other USM institutions on their telework policy | 30% increase in employees who use some type of permanent telework options
Modify existing policy to make it more comprehensive and concise
Get proper approval- VP of Admin & Finance, Staff Council and Union, University Council and Cabinet
Encourage teleworking for employees
Revise telework forms and process forms
Create an online booking tool for booking air travel, hotel reservations and car rentals | N/A | Travel | Fall 2020-Summer 2021 | Meet with Globetrotter Travel to create an online booking tool. | Online booking service provided
Implement online booking tool
Promote and encourage use among employees
Develop a travel workshop presentation to educate campus on current travel policy guidelines including promotion of ways to reduce our air travel carbon footprint. | N/A | Travel | Spring 2021 | Develop presentation to include tips on how to improve carbon footprint when flying and airlines that are the 'greenest' | Number of participants in training sessions
Pilot presentation & gain approval
Coordinate presentations with Campus calendar

## Goal 5
Goal 5- Continue sustainable environmental and landscaping actions
Action | Supporting goal | Responsible Dept/s | Time Frame | Tasks (description of steps): | Measure of success
Create and sustain Campus Garden | N/A | Auxiliary Services | Fall 2021 | Identify a space on campus in which the garden can be planted | Operational garden with comprehensive activities calendar
Engage expert horticulturist to ensure long term viability of garden
Create a BSU Garden Club
|  | C4 |  | Create activities around planting and use of items grown in the garden
Ensure there is minimal food waste from garden items
Collaborate with Wellness Center, Facilities Management, and University Advancement
|  | Student Life/Greek Life |  | Create and plant garden
Create compost heap to create organic fertilizer | N/A | Facilities Management | Spring 2022 | Find location and create shallow trench | Approximate amount (in pounds) of organic fertilizer produced
Lay landscape fabric and borders in trenched area
Dump; landscape debris in the trench out as landscape work progresses creating a compost heap
Regularly turn the debris using the backhoe.
Plant additional trees on campus (20-30) | N/A | C4 | Fall 2020 | Apply for funding with agency/agencies | Number of new trees
Identify spaces on campus where additional trees can be planted
Get final approval from Facilities and VP (Admin & Finance)
|  | Facilities Management |  | Coordinate site visit with appropriate agency
Coordinate irrigation system and installation
Schedule, plan, and promote planting event
|  | Student Life/Greek Life |  | Planting of trees
Initiate a comprehensive BSU 'Keep our Campus' & Recycle campaign | N/A | C4 | Spring 2021 | Collaborate meeting with C4, Res Life and Greek Life | Less visible trash across campus
|  |  |  | Create draft proposal and obtain approval of VPs | Less contamination of recycle bins
Create a leadership group of students from various entities
|  | Residence Life |  | Create short video for clean up
Create short video for Recycling
Meet with URM for any advice, pointers, roll out methods, and branding
|  | Student Life/Greek Life |  | Create promotion through other various sources of media
Rollout of new campaign
Increase electric vehicle charging options on campus | N/A | Facilities Management | Summer 2021- Summer 2023 | Meet with BG&E to determine plan | Double amount of EV chargers on campus
Identify personnel (Communications, Facilities, Sustainability, Campus Safety)
Review the plan
Sign off on site proposal
|  | Procurement |  | Allow BGE to create detailed design package & Right of way agreement
Final design package to be signed
Construction begins

## RESILIENCE
RESILIENCE
RESILIENCE | Supporting goal | Responsible Dept/s | Time Frame | Tasks (description of steps): | Measure of success
Update mechanical, electrical, and plumbing (MEPS) systems, continue to improve fresh air ventilation, and allow for better response to seasonal temperature extremes | Goal 2 | Facilities Management | Spring 2020- Fall 2025 | Survey buildings to determine priority needs for upgraded systems | Number of buildings with replaced or improved systems
|  |  |  | Assess best systems needed for specified buildings | Lowered utitlity bills in building
RFP process for best vendors
Select vendors and secure funding sources
Implement work schedule for vendors and design notifications to building occupants/campus
Work commences in buildings
Undergo campuswide project to replace old and leaky roofs of several buildings | Goal 2 | Facilities Management | Summer 2020- Fall 2020 | Survey and access the existing roof | Replaced roofs
|  |  |  | Provide specifications for design | Lowered utility bills due to improved efficiency
Roofing contractor to remove existing roof
Install new roof
Increase power system reliability and renewability including investment in battery systems, appropriately placed backup/emergency generators, and update monitoring alert systems | N/A | Facilities Management | Summer 2020- Spring 2021 | Determine which buildings and systems require renewability | Number of renewed systems in place
RFP process for best vendors
Procure equipment
Install workstations, gateway cards, and generators appropriately
Significantly increase campus information technology infrastructure for support of alternative work and teaching arrangements to allow continued productivity during extreme weather or pandemic related events | N/A | DIT | Spring 2020-Spring 2022 |  | Less visible trash across campus
Less contamination of recycle bins
Academic Affairs
Create promotion through other various sources of media
Rollout of new campaign